## O2C REPORT STATUS
SL | Scope | Report Name | ABFL-Status | Remarks-ABFL | Formate Status | System Upload | SP Name | CR Status | LIL QC | Findings From QC
1 | Distribution(GDN) | Adjustment DO | Hold |  | Waiting | Uploaded | sal_Rpt_Cr_Proc_Adjustment_Order
2 | Distribution(GDN) | DO Cancel | Done | 1. Cristal report not allowed. Coz we need to work at Excel, Please provide us report in excel download 2. Report data not showing properly as per filter 3. Grand total needed at bottom | Received | Uploaded | sal_Rpt_Cr_Proc_DO_Cancel
3 | Distribution(GDN) | DO Format | Done |  | Received | Uploaded | sal_Rpt_Cr_Proc_Delivery_Order
4 | Distribution(GDN) | DO Delivery and Undelivery | Not Delivered |  | Received
5 | Distribution(GDN) | Item Status (Transfer) | Done | 1. Cristal report not allowed. Coz we need to work at Excel, Please provide us report in excel download | Received | Uploaded | sal_Rpt_Cr_Proc_Item_Transfer
6 | Distribution(GDN) | STR-STO-STN-TRANSFER AGAINST STN(Transfer Receive Summary) | Done | Done | Received | Uploaded | sal_Rpt_Cr_Proc_Stock_Trans_Req_Order_Rcv
| Distribution(GDN) | STR-STO-STN-TRANSFER AGAINST STN(Transfer Issue Summary) | Done | Done
7 | Distribution(GDN) | TRANSPORT(Transfer Bill) | Done | Report not found in 100 | Received | Uploaded | sal_rpt_cr_proc_transport_bill sal_rpt_cr_proc_transport_bill_customer
8 | Distribution(GDN) | Undelivered DO LIST | Done | 1. Grand total row needed 2. After excel export, report main header missing | Received | Under Development | sal_Rpt_Cr_Proc_Undelivered_DO
9 | Distribution(GDN) | DO Notification Report | Discussion |  | Received | Uploaded
10 | Distribution(GDN) | National Stock Availability | Not Delivered |  | Received
11 | Distribution(GDN) | Stock ledger | Done | Total | Received | Uploaded
18 | Distribution(GDN) | Daily Stock report | Done | Data not found | Received
32 | Distribution(GDN) | Delivery Challan | Done |  | Received | Uploaded
16 | Sales Accounts | Customer wise Transaction & AR position | Not Delivered |  | Received
17 | Sales Accounts | Item wise commercial and Inter company sales Report | Done | Right grand total need qty & Value Item code needed SL no | Received | Uploaded
19 | Sales Accounts | Sales Return Report | Done | 1. See report format for feedback 2. Return Value needed at Challan register report | Received | Uploaded | sal_Rpt_Html_Proc_Sales_Return_Report
20 | Sales Accounts | Bank wise collection Report | Done | Please reconcile any bank data for report testing. Grand total needed | Received | Uploaded | sal_Rpt_Proc_Bank_Wise_Collection
21 | Sales Accounts | DO Report | Done | Already done | Received | Uploaded | sal_Rpt_Proc_Delivery_Order
22 | Sales Accounts | Sales report | Done | Already done | Received | Uploaded | sal_Rpt_Proc_Delivered_Invoice
23 | Sales Accounts | Undelivered DO Report/List | Done | 1. Grand total row needed 2. After excel export, report main header missing | Received | Uploaded | sal_Rpt_Proc_Un_Delivery_Order
24 | Sales Accounts | Company wise collection report | Not Delivered |  | Received | Uploaded
25 | Sales Accounts | Customer Credit Limit Status Report | Not Delivered |  | Received | Uploaded
26 | Sales Accounts | Customer wise AR position | Not Delivered |  | Received | Uploaded
27 | Sales Accounts | Customer wise sales and collection | Done | Report Done | Received | Uploaded
28 | Sales Accounts | Customer wise sales and Credit Limit Analysis | Not Delivered |  | Received
29 | Sales Accounts | Customer's credit limit analysis | Not Delivered |  | Received
30 | Sales Accounts | Stuck Customers' Report | Not Delivered |  | Received
33 | Sales Accounts | Sales Order work with me | Done |  | Received | Uploaded
34 | Sales Accounts | Customer Invoice | Done |  | Received | Uploaded
12 | Sales Admin | Sales & Technical Monthly Target vs Achievement | Discussion |  | Received | Uploaded
13 | Sales Admin | Sales & Technical Monthly Target vs Achievement (by category) | Discussion |  | Received | Uploaded
14 | Sales Admin | Sales & Technical Monthly Target vs Achievement (region) | Discussion |  | Received | Uploaded
15 | Sales Admin | Zone Wise Payment & CR % | Not Delivered |  | Received | Uploaded
31 | Sales Accounts | Daily Agent Wise AR Position Report | Done | OB,CB problem | Received | Uploaded

## O2C REPORT STATUS_ALVEE
SL | Scope | Report Name | ABFL-Status | STATUS 22-OCT-23 | Remarks-ABFL
9 | Distribution(GDN) | DO Notification Report | Discussion
12 | Sales Admin | Sales & Technical Monthly Target vs Achievement | Discussion
13 | Sales Admin | Sales & Technical Monthly Target vs Achievement (by category) | Discussion
14 | Sales Admin | Sales & Technical Monthly Target vs Achievement (region) | Discussion
2 | Distribution(GDN) | DO Cancel | Done | Done
3 | Distribution(GDN) | DO Format | Done
5 | Distribution(GDN) | Item Status (Transfer) | Done | Done
6 | Distribution(GDN) | STR-STO-STN-TRANSFER AGAINST STN(Transfer Receive Summary) | Done | No Data Found
| Distribution(GDN) | STR-STO-STN-TRANSFER AGAINST STN(Transfer Issue Summary) | Done | Done
7 | Distribution(GDN) | TRANSPORT(Transfer Bill) | Done | No Data Found
8 | Distribution(GDN) | Undelivered DO LIST | Done | Done | sales -> Undelivered DO report
11 | Distribution(GDN) | Stock ledger | Done | Done
18 | Distribution(GDN) | Daily Stock report | Done | No Data Found
32 | Distribution(GDN) | Delivery Challan / Challan register | Done | Done
17 | Sales Accounts | Item wise commercial and Inter company sales Report | Done | Done | Right grand total need qty & Value Item code needed SL no
19 | Sales Accounts | Sales Return Report | Done | Done | 1. See report format for feedback 2. Return Value needed at Challan register report
20 | Sales Accounts | Bank wise collection Report | Done | No Data Found | Please reconcile any bank data for report testing. Grand total needed
21 | Sales Accounts | DO Report | Done |  | Already done
22 | Sales Accounts | Sales report | Done |  | Already done
23 | Sales Accounts | Undelivered DO Report/List | Done | Done | 1. Grand total row needed 2. After excel export, report main header missing
27 | Sales Accounts | Customer wise sales and collection | Done |  | Report Done
33 | Sales Accounts | Sales Order work with me | Done
34 | Sales Accounts | Customer Invoice | Done
31 | Sales Accounts | Daily Agent Wise AR Position Report | Done |  | OB,CB problem
1 | Distribution(GDN) | Adjustment DO | Hold
4 | Distribution(GDN) | DO Delivery and Undelivery | Not Delivered
10 | Distribution(GDN) | National Stock Availability | Not Delivered
16 | Sales Accounts | Customer wise Transaction & AR position | Not Delivered
24 | Sales Accounts | Company wise collection report | Not Delivered
25 | Sales Accounts | Customer Credit Limit Status Report | Not Delivered
26 | Sales Accounts | Customer wise AR position | Not Delivered
28 | Sales Accounts | Customer wise sales and Credit Limit Analysis | Not Delivered
29 | Sales Accounts | Customer's credit limit analysis | Not Delivered
30 | Sales Accounts | Stuck Customers' Report | Not Delivered
15 | Sales Admin | Zone Wise Payment & CR % | Not Delivered